## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
TEAM NAME | SSAD 46
PROJECT NAME | Surrogate City Finder Tool
PROJECT MENTOR | Dr Vishal Garg
TEAM MEMBERS | Arushi Vashist
Akanksha
Siddharth Bhatore
Dhruva Das
Ayush Tripathi

## Team_Status
TEAM NAME | SSAD 46
PROJECT NAME | Surrogate City Finder Tool
PROJECT MENTOR | Dr Vishal Garg
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Learn ROR | Preparation | All | 4 |  | Ongoing
Role preferences | Coordination | All | 0.5 | 0.3 | Done |  | 0.2 | 66.66666667
Bitbucket Repository | Preparation | All | 1 | 1.5 | Done |  | -0.5 | 33.33333333
Develop Project plan Document | Documentation | Siddharth | 5 |  | Done
Meet and Discuss requirements with client | Preparation | All | 1.5 | 1 | Done |  | 0.5 | 50
Research Technology | Preparation | Arushi | 2 | 1.5 | Ongoing |  | 0.5 | 33.33333333
Project synopsis writeup | Documentation | Dhruva | 2 | 2 | Done |  | 0 | 0
Identify role owners | Preparation | Ayush | 1 | 0.6 | Done |  | 0.4 | 66.66666667
Team Meeting | Coordination | All | 1 | 2 | Done |  | -1 | 50
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Week 7 (sept 12 - sept 18)
Learn ROR | Preparation | All | 10 | 10 | Ongoing |  | 0 | 0
Testing Google Map APIs For Project | Testing | Arushi | 5 | 5 | Ongoing |  | 0 | 0
Software Requirements Specification Document | Requirements | All | 2 | 4 | Done |  | -2 | 50
Get Weather Data for Project | Development | Akanksha | 2 | 2 | Done |  | 0 | 0
Start Implementing Project | Interfaces | Arushi,Dhruva | 2 | 2 | Planned |  | 0 | 0
Team Meeting | Coordination | Dhruva,Siddharth,Ayush | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | All | 1 | 0.5 | Done
Week 8 (sept 19 - sept 25)
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15
Week 16
Week 17

## Individual_Status
TEAM NAME | SSAD_46
PROJECT NAME | SURROGATE CITY
PROJECT MENTOR | DR. VISHAL GARG
Actvities | ARUSHI VASHIST |  | AKANKSHA |  | SIDDHARTH |  | AYUSH TRIPATHI |  | DHRUVA DAS |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 6 (sept 5- sept 11)
Learning basics of ROR | 2-3 hours |  | 2-3 hours |  | 4-5 hours | 3-4 hours | 3-4 hours | 4 1/2 - 5 hours | 3-4 hours | 4-4 1/2 hours | 15-20 hours | #VALUE!
Role preferences | 1 hour |  | 1 hour |  | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 5 hours | #VALUE!
Bitbucket Repository | 30 minutes |  | 45 minutes |  | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 30 minutes | 3 hours 30 minutes | #VALUE!
#REF! | 30 minutes |  | 30 minutes |  | 30 minutes | 30 minutes | 30 minutes | 40 minutes | 30 minutes | 45 minutes | 2 hours 30 minutes | #VALUE!
Develop Project plan Document | 1 hour |  | 1 hour |  | 1 hour | 1.5 hour | 1 hour | 1 hour | 1 hour | 1 hour 30 min | 2 hours 30 minutes | #VALUE!
Meet and Discuss requirements with client | 1 hour |  | 1 hour |  | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 2 hours 30 minutes | #VALUE!
Research Technology | 1 hours |  | 2 hours |  | 3 hours | 2 hour | 1 hour and 30 minutes | 4-5 hours | 3 hours | 4 hours | 10 hours 30 minutes | #VALUE!
Project synopsis writeup | 40 minutes |  | 50-55 minutes |  | 1 hour | 45 minutes | 45 minutes | 1 hour | 45 minutes | 1 hour | 4 hours 15 minutes to 4 hours 20 minutes | #VALUE!
Identify role owners | 20 minutes |  | 20 minutes |  | 20 minutes | 20 minutes | 30 minutes | 30 minutes | 20 minutes | 20 minutes | 1 hour 50 minutes | #VALUE!
Team Meeting | 45 minutes |  | 45 minutes |  | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 1 hour | 3 hours 45 minutes | #VALUE!
Status tracker | 15 minutes |  | 15 minutes |  | 15 minutes | 45 minutes | 15 minutes | 15 minutes | 15 minutes | 30 minutes | 1 hour 15 minutes | #VALUE!
Week 7 (sept 12 - sept 18) | 0 | 0 | 0 | 0 | 0 | 0
Learning basics of ROR | 2-3 Hours | 4-5 Hours | 2-3 Hours | 4-5 hours | 2-3 hours | 4-5 hours | 3-4 hours | 7-8 hours | 3-4 hours | 4-5 hours | #VALUE! | #VALUE!
Testing Google Map API | 5-6 Hours | 8 Hours | 1 Hour | 1 Hour | [6 empty] | #VALUE! | #VALUE!
Fetching Data Files | 1 Hours | 1 Hour | 2-3 Hours | 4-5 hours | 1 hour | 2 hours |  |  | 1-2 hours | 2 hours | #VALUE! | #VALUE!
Making Database | 1 Hours | - |  |  |  |  | 2 hours |  |  |  | #VALUE! | 0
Refining knowledge of requirements | 2 Hours | 2 Hours | 2 Hours | 2 Hours | 2 hours | 3 hours | 2 hours | 3 hours | 2 hours | 3 hours | #VALUE! | #VALUE!
SRS Document |  |  | 2 Hours | 3 Hours | 2-3 hours | 6-7 hours | 3 hours | 5 hours | 2 hours | 4-5 hours | #VALUE! | #VALUE!
Team Meeting | 1 Hour | 1 Hours | 1 Hour | 1 Hours | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour
Status Tracker | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 30 minutes | 30 minutes | 1 hours 30 minutes | 15 minutes | 45 minutes
Week 8 (sept 19 - sept 25)
Learning basics of ROR | 2-3 Hours | 4-5 Hours | 2-3 Hours | 4-5 hours | 2-3 hours | 4-5 hours | 3-4 hours | 7-8 hours | 3-4 hours | 4-5 hours | #VALUE! | #VALUE!
Testing Google Map API | 5-6 Hours | 8 Hours | 1 Hour | 1 Hour | [6 empty] | #VALUE! | #VALUE!
Fetching Data Files | 1 Hours | 1 Hour | 2-3 Hours | 4-5 hours | 1 hour | 2 hours |  |  | 1-2 hours | 2 hours | #VALUE! | #VALUE!
Making Database | 1 Hours | - |  |  |  |  | 2 hours |  |  |  | #VALUE! | #VALUE!
Refining knowledge of requirements | 2 Hours | 2 Hours | 2 Hours | 2 Hours | 2 hours | 3 hours | 2 hours | 3 hours | 2 hours | 3 hours | #VALUE! | #VALUE!
SRS Document |  |  | 2 Hours | 3 Hours | 2-3 hours | 6-7 hours | 3 hours | 5 hours | 2 hours | 4-5 hours | #VALUE! | #VALUE!
Team Meeting | 1 Hour | 1 Hours | 1 Hour | 1 Hours | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | #VALUE! | #VALUE!
Status Tracker | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 30 minutes | 30 minutes | 1 hours 30 minutes | 15 minutes | 45 minutes | #VALUE! | #VALUE!
[11 empty] | 0 | 0
[11 empty] | 0 | 0
Week 9 | [10 empty] | 0 | 0
Learning basics of ROR | 2-3 Hours | 4-5 Hours | 2-3 Hours | 4-5 hours | 2-3 hours | 4-5 hours | 3-4 hours | 7-8 hours | 3-4 hours | 4-5 hours | #VALUE! | #VALUE!
Testing Google Map API | 5-6 Hours | 8 Hours | 1 Hour | 1 Hour | [6 empty] | #VALUE! | #VALUE!
Fetching Data Files | 1 Hours | 1 Hour | 2-3 Hours | 4-5 hours | 1 hour | 2 hours |  |  | 1-2 hours | 2 hours | #VALUE! | #VALUE!
Making Database | 1 Hours | - |  |  |  |  | 2 hours |  |  |  | #VALUE! | #VALUE!
Refining knowledge of requirements | 2 Hours | 2 Hours | 2 Hours | 2 Hours | 2 hours | 3 hours | 2 hours | 3 hours | 2 hours | 3 hours | #VALUE! | #VALUE!
SRS Document |  |  | 2 Hours | 3 Hours | 2-3 hours | 6-7 hours | 3 hours | 5 hours | 2 hours | 4-5 hours | #VALUE! | #VALUE!
Team Meeting | 1 Hour | 1 Hours | 1 Hour | 1 Hours | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | #VALUE! | #VALUE!
Status Tracker | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 30 minutes | 30 minutes | 1 hours 30 minutes | 15 minutes | 45 minutes | #VALUE! | #VALUE!
Week 10 | [10 empty] | 0 | 0
Week 11 | [10 empty] | 0 | 0
Week 12 | [10 empty] | 0 | 0
Week 13 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
Week 14 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
Week 15 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
Week 16 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
Week 17 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0